## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-20 | 2022-10-21
|  | Day 0 | Day 4 | Day 5
7 | Review Pattern 1 | 0.2 | 0.2
8 | Review Pattern 2 | 0.2 | 0.2
9 | Review Pattern 3 | 0.2 | 0.2
10 | Review Smell 1 | 0.1 | 0.1
11 | Review Smell 2 | 0.1 | 0.1
12 | Review Smell 3 | 0.1 | 0.1
Completed Effort |  | 0 | 0.9 | 0.9
Remaining Effort |  | 0.9 | 0 | 0
Ideal Burndown |  | 0.9 | 0.45 | 0